## Work Plan
|  |  | 01.10.2020-07.10.2020 | 08.10.2020-14.10.2020 | 15.10.2020-21.10.2020 | 22.10.2020-28.10.2020 | 29.10.2020-04.11.2020 | 05.11.2020-11.11.2020 | 12.11.2020-18.11.2020 | 19.11.2020-25.11.2020 | 26.11.2020-02.12.2020 | 03.12.2020-09.12.2020 | 10.12.2020-16.12.2020 | 17.12.2020-23.12.2020 | 24.12.2020-30.12.2020 | 31.12.2020-05.01.2021
Start Date: 26/10/2020 | ASSIGNEE(s) |  | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13 | WEEK 14
Literature Review |  | Week (1-4) | bar: WEEK 1 to WEEK 4
Research | İLKİN GAMZE ÖZEL & DAMLA TEZEL & UMUT BOZDOĞAN | bar: WEEK 1 to WEEK 3
Evaluate Reasearches | İLKİN GAMZE ÖZEL & DAMLA TEZEL & UMUT BOZDOĞAN | bar: WEEK 1 to WEEK 3
Conclude | İLKİN GAMZE ÖZEL & DAMLA TEZEL & UMUT BOZDOĞAN | bar: WEEK 4
Software Requirements Specification |  | Week (5-9) | bar: WEEK 5 to WEEK 9
Identily SRS | İLKİN GAMZE ÖZEL | bar: WEEK 5 to WEEK 7
Develop Use Cases | UMUT BOZDOĞAN | bar: WEEK 5 to WEEK 7
Evaluate & Edit SRS | DAMLA TEZEL | bar: WEEK 8 to WEEK 9
Project Webpage |  | Week (10) | bar: WEEK 10
Specily General Webpage Concept | İLKİN GAMZE ÖZEL & DAMLA TEZEL & UMUT BOZDOĞAN | bar: WEEK 10
Develop the Webpage | İLKİN GAMZE ÖZEL & DAMLA TEZEL & UMUT BOZDOĞAN | bar: WEEK 10
Software Design Description |  | Week (7-12) | bar: WEEK 7 to WEEK 12
Develop Mockup for Web | İLKİN GAMZE ÖZEL | bar: WEEK 7 to WEEK 11
Develop Mockup for Android & iOS | UMUT BOZDOĞAN | bar: WEEK 7 to WEEK 11
Test & Release | UMUT BOZDOĞAN | bar: WEEK 11
Specify UML Diagrams | DAMLA TEZEL | bar: WEEK 11
Create UML Diagrams | DAMLA TEZEL | bar: WEEK 11
Evaluate and Edit SDD | İLKİN GAMZE ÖZEL & DAMLA TEZEL & UMUT BOZDOĞAN | bar: WEEK 11 to WEEK 12
Test & Release | İLKİN GAMZE ÖZEL | bar: WEEK 11 to WEEK 12
Project Report & Presentation |  | Week (11-14) | bar: WEEK 11 to WEEK 14
Edit Project Report | İLKİN GAMZE ÖZEL & DAMLA TEZEL & UMUT BOZDOĞAN | bar: WEEK 11 to WEEK 14
Prepare Presentation | İLKİN GAMZE ÖZEL & DAMLA TEZEL & UMUT BOZDOĞAN | bar: WEEK 11 to WEEK 14